## Project schedule
GANTT-CHART TASQ GETTING STEAM
[7 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01
NR. | TASK | ASSIGNED TO | PROGRESS | START | END |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| WP 1- Management, organisation & administration | SAT
1.1 | Settingup the project | SAT | 0% | 2025-09-01 | 2025-10-01 | 31 | bar: 2025-09-01
1.2 | Start up meeting | SAT | 0% | 2025-10-01 | 2025-11-01 | 32 | bar: 2025-10-01
1.3 | regular steering group meeting | SAT | 0% | 2025-11-01 | 2028-06-01 | 944 | bar: 2025-11-01; 2026-02-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-05-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-05-01
1.4 | regular project team meeting WP 2 | SAT | 0% | 2028-06-01 | 2028-08-01 | 62 | bar: 2025-10-01; 2025-12-01; 2026-03-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-04-01; 2027-06-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-04-01; 2028-06-01
1.5 | regular project team meeting WP 3 | SAT | 0% | 2025-09-01 | 2028-08-02 | 1067 | bar: 2025-10-01; 2025-12-01; 2026-03-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-04-01; 2027-06-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-04-01; 2028-06-01
1.6 | regular project team meeting WP 4 | SAT | 0% | 2025-09-01 | 2028-08-03 | 1068 | bar: 2025-10-01; 2025-12-01; 2026-03-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-04-01; 2027-06-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-04-01; 2028-06-01
1.7 | regular project team meeting WP 5 | SAT | 0% | 2025-09-01 | 2028-08-04 | 1069 | bar: 2025-10-01; 2025-12-01; 2026-03-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-04-01; 2027-06-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-04-01; 2028-06-01
1.8 | evaluation moments | SAT | 0% | 2025-09-01 | 2028-08-05 | bar: 2025-11-01; 2026-02-01; 2026-05-01; 2026-09-01; 2026-11-01; 2027-02-01; 2027-05-01; 2027-09-01; 2027-11-01; 2028-02-01; 2028-05-01
| WP 2 - Education future TASQ professionals | SAT
2.1 | Education for teachers in Armenia into TASQ teacher | SAT | 0% | 2025-09-01 | 2025-11-30 | 91 | bar: 2025-09-01 to 2025-11-01
2.2 | Establishing of Armenian community of TASQ-practice | SAT | 0% | 2025-09-03 | 2028-04-01 | 942 | bar: 2025-12-01; 2026-04-01; 2026-09-01; 2026-12-01; 2027-04-01; 2027-09-01; 2027-12-01; 2028-04-01
2.3 | Learning, teaching & training (LTTA) activity from Armenia to BCE | SAT | 0% | 2025-09-01 | 2028-03-01 | 913 | bar: 2026-03-01; 2027-03-01; 2028-03-01
2.4 | Coaching VET teachers to TASQ teacher | SAT | 0% | 2025-09-01 | 2028-09-01 | 1097 | bar: 2025-09-01 to 2025-12-01; 2026-02-01 to 2026-06-01; 2026-09-01 to 2026-12-01; 2027-02-01 to 2027-06-01; 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-06-01
2.5 | LTTA activity education policy stakeholders to the Netherlands | SAT | 0% | 2025-11-01 | 2025-11-04 | 4 | bar: 2025-11-01
| WP 3 - Establishing TASQ learning environments in Armenian VET schools | SOA
3.1 | Building the knowledge basis for physical learning environments of Armenian TASQ schools |  | 0%
3.1.1 | Model for TASQ Learning Environment | SOA | 0% | 2025-09-01 | 2026-02-01 | 154 | bar: 2025-09-01 to 2025-12-01; 2026-02-01
3.1.2 | Provide theoretical and real experience of Technasium learning environments | SOA | 0% | 2026-01-01 | 2026-06-01 | bar: 2026-02-01 to 2026-04-01
3.2 | Co-creation of innovative learning environments at 4 Armenian VET schools to become TASQ schools |  | 0%
3.2.1 | Develop innovative TASQ learning environments | SOA | 0% | 2026-05-01 | 2027-01-01 | bar: 2026-05-01 to 2026-06-01; 2026-09-01 to 2026-12-01
3.2.2 | Adapting learning spaces | SOA | 0% | 2026-10-01 | 2027-04-01 | bar: 2026-10-01 to 2026-12-01; 2027-02-01 to 2027-04-01
3.2.3 | Successful implementation | SOA | 0% | 2027-03-01 | 2028-02-01 | bar: 2027-03-01 to 2027-06-01; 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-04-01
3.3 | Develop a TASQ toolkit for Armenian schools |  | 0%
3.3.1 | Developing the main design of the TASQ Toolkit | SOA | 0% | 2027-04-01 | 2027-09-01 | bar: 2027-04-01 to 2027-06-01; 2027-09-01
3.3.2 | Description of the different learning spaces and relations | SOA | 0% | 2027-06-01 | 2027-11-01 | bar: 2027-06-01; 2027-09-01 to 2027-11-01
3.3.3 | Tools for implementation | SOA | 0% | 2027-08-01 | 2028-02-01 | bar: 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-04-01
| WP 4 - VET Students in TASQ Getting STEAM | ATSEC
4.1 | Material for projects | ATSEC | 0% | 2025-09-01 | 2028-08-01 | bar: 2025-09-01 to 2025-12-01; 2026-02-01 to 2026-06-01; 2026-09-01 to 2026-12-01; 2027-02-01 to 2027-06-01; 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-06-01
YEAR 1
4.2 | Workshops (fe #D printing, laser cutting) | ATSEC | 0% | 2025-09-01 | 2025-11-01 | bar: 2025-09-01 to 2025-11-01
4.2.1 | Project | ATSEC | 0% | 2025-11-01 | 2026-02-01 | bar: 2025-12-01; 2026-02-01
4.2.2 | Workshop | ATSEC | 0% | 2026-02-01 | 2026-03-01 | bar: 2026-03-01 to 2026-04-01
4.2.3 | Project | ATSEC | 0% | 2026-04-01 | 2026-05-01 | bar: 2026-04-01 to 2026-05-01
4.2.4 | Summer vacation | ATSEC | 0% | 2026-06-01 | 2026-06-01 | bar: 2026-06-01
YEAR 2
4.2.5 | Project | ATSEC | 0% | 2026-09-01 | 2026-11-01 | bar: 2026-09-01 to 2026-11-01
4.2.6 | Workshop | ATSEC | 0% | 2026-11-01 | 2026-12-01 | 31 | bar: 2026-11-01 to 2026-12-01
4.2.7 | Project | ATSEC | 0% | 2026-12-01 | 2027-03-01 | bar: 2026-12-01; 2027-02-01 to 2027-03-01
4.2.8 | Workshop | ATSEC | 0% | 2027-03-01 | 2027-03-01 | bar: 2027-03-01
4.2.9 | Project | ATSEC | 0% | 2027-04-01 | 2027-05-01 | bar: 2027-04-01 to 2027-05-01
4.2.10 | Summer vacation | ATSEC | 0% | 2027-06-01 | 2027-06-01 | bar: 2027-06-01
YEAR 3
4.2.11 | Project | ATSEC | 0% | 2027-09-01 | 2027-11-01 | bar: 2027-09-01 to 2027-11-01
4.2.12 | Workshop | ATSEC | 0% | 2027-11-01 | 2027-12-01 | 31 | bar: 2027-11-01 to 2027-12-01
4.2.13 | Project | ATSEC | 0% | 2027-12-01 | 2028-03-01 | bar: 2027-12-01; 2028-02-01 to 2028-03-01
4.2.14 | Workshop | ATSEC | 0% | 2028-03-01 | 2028-03-01 | bar: 2028-03-01
4.2.15 | Project | ATSEC | 0% | 2028-04-01 | 2028-05-01 | bar: 2028-04-01 to 2028-05-01
4.2.16 | Summer vacation | ATSEC | 0% | 2028-06-01 | 2028-06-01 | bar: 2028-06-01
4.3 | Visiting Netherlands | ATSEC | 0% | 2028-03-01 | 2028-04-01 | bar: 2028-03-01 to 2028-04-01
4.4 | Development & implementation electronic Student Portfolios | ATSEC | 0% | 2028-02-01 | 2028-03-01 | bar: 2025-09-01 to 2025-12-01; 2026-02-01 to 2026-06-01; 2026-09-01 to 2026-12-01; 2027-02-01 to 2027-06-01; 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-06-01
| WP 5 - Dissemination & Sustainability | ATSEC
5.1 | Translation Technasium documents into Armenian | ATSEC | 0% | 2025-09-01 | 2028-09-01 | 1097 | 2025-09-01: 5.1
5.2 | Adaption & Implementation Dutch R&D curriculum | ATSEC | 0% | may 26 | 2026-12-01 | #VALUE! | 2026-12-01: 5.2
5.3 | Visibility of VET-activity in the TASQ online platform | ATSEC | 0% | 2025-09-01 | 2028-09-01 | 1097 | bar: 2025-09-01 to 2025-12-01; 2026-02-01 to 2026-06-01; 2026-09-01 to 2026-12-01; 2027-02-01 to 2027-06-01; 2027-09-01 to 2027-12-01; 2028-02-01 to 2028-06-01
5.4 | organisation of 3 multiplier conferences in Armenia | ATSEC | 0% | 2026-06-01 | 2028-06-01 | 732 | bar: 2026-06-01; 2027-06-01; 2028-06-01
5.5 | Organisation of webinar about general TASQ ideas in Armenia | ATSEC | 0% | 2025-09-01 | 2025-09-01 | 1 | bar: 2025-09-01